L’Approche du Cadre Logique

Action Plan Development

Analyse

- Problématique : identifier les problèmes clés, les contraintes et opportunités ; déterminer les relations de cause à effet

- Analyse the specific problems, the constraints and opportunties ; identify the causes and effects.

- Objectifs (Résults): les solutions aux problèmes identifiés

- Set Objectives : Set objectives to provide solutions to the problems identified.

- Parties prenantes : identifier et caractériser les principaux intéressés, définir un système de gestion

- Stakeholders and Participants : Identify and categorise the main interested parties/stakeholders and a management approach.

- Stratégie : identifier des différentes stratégies pour trouver les solutions ; choisir la stratégie mieux adaptée

- Strategy : Identify the strategies for providing solutions ; chose the best strategy for the context.

Planification

- Liste des activités à mettre en oeuvre pour atteindre chaque objectif (Résultat)

- List the activities in an action plan so as to obtain the results  planned.

- Priorités pour la mise en œuvre des activités : quels sont les activités à mettre en place dans les prochains 6 mois ?

- Diffusion des informations

- Ligne de base

- Identification des besoins de formation

- …

- …

- Prioritise these activities ; which ones should be in place in the next 6 months ?

- information sharing about the project

- baseline data collection

- Identify training needs..

- ....

- ...

- Orientations pour la mise en oeuvre : quels sont les actions concrètes à mettre en place pour chaque une des activités ? et qui sont les responsables ?

14. Directions for the Action Plan : what are the sub activities which need to be in place for each of the main activities to happen ? Who is responsible for each sub activity ?

- Organisation dans un chronogramme et budget

- Display the information in a time schedule with a budget.

PLAN D’ACTION DU SITE : CAMEROON

| Activity of global plan | Activity of annual plan | Concrete actions | Start | Budget | Responsible |
| --- | --- | --- | --- | --- | --- |
|  |  |  | D | J | F | M | A | M | J | UNIDO | OTHER |  |
| Project Management | Develop and agree an MoU between UNIDO and MINEP |  |  |  |  |  |  |  |  |  |  | Focal point |
|  | Agree disbursement procedure for GEF funds |  |  |  |  |  |  |  |  |  |  |  |
|  | Advertise, identify and recruit DEMO coordinator |  |  |  |  |  |  |  |  |  |  |  |
|  | Activities review of progress and planning for next year | Hold meeting to evaluate past year work plan |  |  |  |  |  |  |  | 1750 |  | Demo coordinator + Focal point + Site committee |
|  |  | Programme for the next year |  |  |  |  |  |  |  |  |  |  |
|  |  | Identify specific actions to address barriers to implementation |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Undertake baseline survey building on previous research to include key sources of land based contamination- | Develop ToR and cost if necessary |  |  |  |  |  |  |  | 12,000 direct from UNIDO country office | 100 | Coordinator + Focal point + site committee |
|  |  | Recruit consultant/delegate site committee responsabilities |  |  |  |  |  |  |  |  |  |  |
|  |  | Collect data |  |  |  |  |  |  |  |  |  |  |
| 1.1 (Contd) | biodiversity-social stress management | Analyse results and document |  |  |  |  |  |  |  |  |  |  |
|  |  | Propose and identify solutions |  |  |  |  |  |  |  |  |  |  |
|  |  | Use data for sensitisation |  |  |  |  |  |  |  |  |  |  |
|  |  | Implement identified solutions |  |  |  |  |  |  |  |  |  |  |
| 1.2, 1.3, 1.4 | Begin work with selected communities at Grand Batanga, Lobe and Lonji to assess waste management and ecotourism options, cost and begin implementation | Lonji | Initial stakeholder planning meeting |  |  |  |  |  |  |  | 5,000 | 5,000 (Gov.) | Coordinateur + site management committee + focal point |
|  |  |  | Toilet construction (EIA) |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Develop clean market area (EIA) |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Clean beach |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Change fisher people’s bejaviour vis-à-vis pollution |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Production of posters |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Development of waste management system |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Production of information boards |  |  |  |  |  |  |  |  |  |  |
| 1.2, 1.3, 1.4 (Contd.) |  | Lobi falls | Initial planning meeting |  |  |  |  |  |  |  | 5,000 | 5,000 (Gov.) | Coordinateur + site management committee + focal point |
|  |  |  | Development of information boards |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Development of toilets (EAI) |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Private community partnership (boat leasing, restaurants, distribution of drinking water –EAI-) |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Zoning of land |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Development of waste management system (compost recycling) |  |  |  |  |  |  |  |  |  |  |
|  |  | Grand Batanga | Initial planning meeting Encourage SME development (beach restaurants) |  |  |  |  |  |  |  | 5,000 | 5,000 (Gov.) | Coordinateur + site management committee + focal point |
|  |  |  | Toilet construction (EAI) |  |  |  |  |  |  |  |  |  |  |
| 1.2, 1.3, 1.4 (Contd.) |  | Grand Batanga (Contd.) | Waste management mechanism development |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Restaurant development |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Diversifying business opportunities |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Reorganisation of community entrepreneurs-association |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Community-port authority joint venture |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Identify and nominate representatives for the local management committee |  |  |  |  |  |  |  |  |  |  | Focal point |
| 3.1 | Identify and establish an MoU wit a locally base training-research institute | Develop MoU with MEAO to work on recommendations from capacity assessment |  |  |  |  |  |  |  | Regional budget UNIDO |  | Coordinator + local site committee + focal point + MINEP+MEAO |
|  |  | Discuss and develop sub contract for training delivery |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Undertake local capacity assessment and report results to check against proposed activities | Develop ToR and cost |  |  |  |  |  |  |  | Regional budget UNIDO |  | RCU + Demo coordinator + focal point |
|  |  | Facilitate in country meetings |  |  |  |  |  |  |  |  |  |  |
|  |  | Comment on the draft report |  |  |  |  |  |  |  |  |  |  |
|  |  | Ensure recommendations feed into the MoU wit a locally base training-research institute |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Prepare and implement DEMO project awareness raising activities | Plan first dialogue meeting |  |  |  |  |  |  |  |  | 250 | Coordinator + Focal point + site committee |
|  |  | Identify target audience groups |  |  |  |  |  |  |  |  |  |  |
|  |  | Agree what products to produce |  |  |  |  |  |  |  |  | 500 |  |
|  |  | Cost to what has been agreed to produce |  |  |  |  |  |  |  | 700 | 3000 |  |
|  |  | Produce |  |  |  |  |  |  |  |  |  |  |
|  |  | Distribute |  |  |  |  |  |  |  | 410 | 1000 | Same than above + operators |
| 4.5 | Développer des outils d’information sur le projet | Identifier quels outils créer pour diffuser l’information (but à définir) |  |  |  |  |  |  |  |  |  | Coordinateur |
|  |  | Identifier les cibles à informer |  |  |  |  |  |  |  |  |  |  |
|  |  | Identifier la forme de l’information |  |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |

| Coûts opérationnels/Operational Costs | Budget |
| --- | --- |
|  | UNIDO | OTHER |

N.B. Dans la préparation du plan d’action, n’oubliez pas de budgétiser : le salaire du coordinateur, les dépenses liées à la coordination (équipement du bureau, réunions du comité de pilotage, envoi des rapports, etc).

NB> Don’t forget to budget for the office, communication equipment, meetings, report preparation and dissemination, etc.

|  | Budget |
| --- | --- |
|  | UNIDO | OTHER |
| GRAND TOTAL |  |  |