## Slide 1: 5th STEERING COMMITTEE MEETING Bagamoyo, Tanzania 24-27 September, 2013
By: Luzio Nhavene; Maria Cidalia, Esther M. Munyithia
Ecotourism Thematic Component: ST-EP Tourism Initiatives Activities Mozambique
(SCM Day 2: 25 September 2013)
Notes: <number>

## Slide 2
OUTLINE
Project Objectives and planned activities;
Main Project activities carried out so far;
Challenges faced during implementation;
Results achieved so far;
Recommendations:;

## Slide 3
Introduction
The COAST Project is implementing the Ecotourism Component in partnership with Tourism Department and SNV through of implementation the project: MOZAMBIQUE: Supporting Platform for Inhambane ST-EP Tourism Initiatives, PHASE I and II.
The ST-EP mechanism in Mozambique, started in 2008 and was developed many activities on (i) Skills development training through modular courses, (ii) small matching grants and in term of ST-EP mechanisms, was addressed 5 out of 7 mechanism. Also, was developed the Value Chain Analysis in the demo site, which contributed to define priority setting and activities to boost Tourism, Such as:
Development of public-private partnerships, in which government and industry representatives collaborated to promote the destination: (e.g through travel shows, diving event and national and international fair);
The government, in collaboration with private sector partners has worked to develop vocational skills by introducing targeted training for current staff in food preparation and hospitality management;
Other development include ALMA, a local non-Government Organization, which introduced a waste recycling programe to keep tourist areas clean.

## Slide 4
Location:

## Slide 5
  Objective:
  The main objective, is to enhance the local economic impact from tourism in Inhambane-Demo site through human resource development and SME development in the tourism sector.
Planned Activities in The Demo Site:
Support MSE's development in the tourism supply chains, including sectors of arts & crafts, food & beverages and tourism attractions;
Support The implementation of skills development training through modular courses.
Consolidate local Multi Stakeholder Platforms (MSP) in Inhambane with participation of provincial and district governments, private sector, NGOs and communities for joint action;
Project Objectives and Planned Activities

## Slide 6
Planned Activities: (CONT)
The ST-EP mechanisms that was addressed by the project are the following:
Employment of the poor in tourism enterprises;
Supply of goods and services to tourism enterprises by the poor or by enterprises employing the poor;
Direct sales of goods and services to visitors by the poor (informal economy);
Establishment and running of small, micro or community-based tourism enterprises or joint ventures by the poor (formal economy)
Voluntary giving and support by tourists or tourism enterprises

## Slide 7: Skills development training through modular courses.

## Slide 8
  Waste Recycling and Handicraft Programe- ALMA Association;
Small Matching Grants
In term of small matching grants, 6 micro-entrepreneurs out of 15 project have been highly successful in the linking to the tourism supply chain and now are established small business that supply with regularity and quality.

## Slide 9: Small Matching Grants
Production of eggs Project
Sailing boat project
Handcrafts’ production
Vegetable farming
Gastronomy project

## Slide 10
Small Matching Grants

## Slide 11
ST-EP mechanisms.
Provision of clean potable drinking water to the communities of Conguiana, Manhanza and Nhamua, (Demo site), benefiting 800 households/4000 people directly;
Main Project Activities Carried Out so Far

## Slide 12
  ST-EP mechanisms.
  Providing space for small business- arts and crafts-to have direct access to sell to tourists, benefiting 14-20 craft people;
Main Project Activities Carried Out so Far

## Slide 13
  ST-EP mechanisms.
  Improving infrastructure (yearly repair and maintenance of 15 km of rood and building a 200 meter bridge over marshlands), which makes communication and transportation less onerous and saves much time for 1000 local families;
  The Barra Group currently employs 329 employees of which 9 out of 10 are nationals from the surrounding communities. This represents roughly 21% of the total tourism workforce in the Peninsula of Inhambane;
  Built a complete health clinic;
  Primary education through the provision of improved classrooms, school materials for school children and sponsoring education costs for orphaned children, benefiting in total 750-900 school children;
Main Project Activities Carried Out so Far

## Slide 14: Challenges
The need to give more direct assistance to projects benefiting from micro financing/small matching grants.
The need to have the hotel and tourism association playing a major role in the monitoring and facilitation of job opportunities in the tourism sector for the trainees within the province, as well as facilitating attachments for the trainees during training so that they can have some hands on experience.

## Slide 15: Results Achieved
The creation of alternative source of livelihood for fishermen in the community through skill development training, thus contributing to conservation of biodiversity.
Skill and knowledge transfer as well as environment conscious awareness to the community members as in the case of ALMA (the environment association), who recycle waste and make handicrafts out of it involving the community members.
Contribution to the growth of the informal economy through the small matching grants for community projects, while at the same time maximizing the benefits from tourism development for the community.

## Slide 16: Recommendations
Continue to support the value chain initiatives in tourism, involving the local communities so that they directly benefit from tourism development.
A more flexible system in regard to transfer of funds so as to avoid delays in subsequent activities.
The extension of the ST-EP mechanism in other provinces in the country that have a high tourism potential.

## Slide 17
Thanks
Contacts:
FP Tourism:
Ms. Maria Cidalia
cida72cida@yahoo.com.br
Liaison Officer COAST Project:
Ms Esther M. Munyithia emunyithia@yahoo.com
DPC: : Luzio Nhavene luzhavene@gmail.com
Notes: <number>