## Slide 2
BACKGROUND
The name of the project is SUSTAINABLE ECOTOURISM ENHANCEMENT FOR POVERTY ALLEVIATION AND BIODIVERSITY CONSERVATION
The project is implemented in Bagamoyo Demosite at Dunda, Kaole and Mlingotini

## Slide 3
Total Budget from COAST :USD 50,000
The Project is Implemented by Bagamoyo District Council
PROJECT OBJECTIVE
Capacity building for local communities in sustainable marine & coastal resource management for income Generation and improvement of livelihoods

## Slide 4
PROJECT ACTIVITIES IN BRIEF
Awareness campaigns in the project area (Kaole, Dunda, Mlingotini) involving members of the community and other ecotourism stakeholders
Tailor made trainings/skills development for tourism stakeholder groups (tour guides, handicraft producers, boat operators, food vendors /homestay providers, local performance entertainment groups

## Slide 5
Setting up of tourist information office, promotional material development (brochures/flyers/website)
Promotion and marketing
Support to environmental protection / conservation initiatives
Facilitation of establishment of tourism stakeholder dialogue forum
PROJECT EXPECTED OUTPUT
Increased community awareness on the potential of tourism and biodiversity conservation;

## Slide 6
Increased income generation from activities and enhanced local entrepreneurship;
Improved service delivery;
Increased tourist arrivals;
Improved beach and marine environment;
Increased tourism stakeholders’ collaboration (between District authority, local communities, private sector and NGOs)

## Slide 7
PROJECT CURRENT STATUS AND OUTPUTS
Education and awareness workshops at the project area (Dunda, Kaole and Mlingotini)
Education and awareness campaigns at schools in the project area
Training for handcraft groups in quality improvement
Training in improvement in accommodation, hospitality, food safety, food provision services

## Slide 8
Workshop in marine products improvements & hygiene, fishing/seaweed farming groups
Tourism enterprise coordinators’ cross learning visit to CTP enterprise
Training in guiding, basic environmental education and interpretive skills for 12 guides
Make and place sign boards
Assessment of areas for mangroves replanting with community members, community resource mapping
Mobilization of people and planting
Notes: <number>

## Slide 9
Participation in a local tourism event (Karibu Travel tourism Fair-Arusha)
Management business skills training for tourism enterprise coordinators, cultural tour coordinators, food/home-stay providers, curio sellers, fishermen groups
Development of brochures for promoting tourism in Bagamoyo.

## Slide 10
Fields surveys involving foot traffic count and catchment study to 3 in-demand/potential areas for eco-tourism enterprise establishment.

## Slide 11
Results achieved so far.
Awareness in the three villages and 6 schools on the Project and tourism potential in their village has been raised
Positive reception of the project by the community.
Formulation of 6 Ecotourism clubs in 6 primary schools
25 handcrafts have bee trained on Product improvement and business skill
Improvement of local food delivery services to tourist and visitors

## Slide 12
Improvement in Seaweed farming and fish processing practices (Processes and Business)
Learning of Best practices on cultural tourism enterprise in Arusha (12 people benefited)
26 tour guides are trained on basic environmental education to improve their working skill with environmental concern (Tour guides trainee formulated their club)
Improvement of Public-Private Partnership in tourism industry . Bagamoyo DC&TC,TCMP, tourist companies and Hotels.
Recruitment of Tourism Officer in Bagamoyo.

## Slide 13
Promotion of tourist attractions through Participation in a local tourism event (Karibu Travel tourism Fair-Arusha);
Aproximatelly15 acres of mangroves were replanted within project area.
Establishment of 2 cultural tourism enterprise
21 people have been trained on Management of business skills on tourism activities.

## Slide 14
Challenges encountered during implementation
Large interested community to be trained with limited funds to support
Most of the challenges are internal which we are supposed to deal with ourselves (Bureaucratic procedures to handle request, transport facilities; etc)

## Slide 15
Recommendations for further activities to help increase socio-economic benefits from tourism in coastal destinations in the country
Extension of the project time frame will bring more positive impacts to the community.
Up scaling of the project to other villages for widespread positive impact to the community
More training is needed to unveil the tourism potentials in the area

## Slide 16
Other stakeholders are needed to complement on capacitating people with resources (Loans, grants) to run small tourism business.
More funds to facilitate the established cultural tourism enterprise.
Identification of new tourist products.