PROPOSED ACTIVITIES- 1ST- 2ND QUARTER (FY 2010/11) – WATAMU DEMO SITE

|  | Proposed activity | Requirements | Unit cost | Total cost (Ksh) |
| --- | --- | --- | --- | --- |
| 1 | Holding 4 consultative meetings with stakeholders to constitute Watamu DEMO site management committee | Lunch allowances 5pax *4 Days Fuel 50lit* 4 days Refreshments/teas/ stationery 20 pax*4 Days | 1000 100 500 | 20,000 20,000 40,000 |
| 2 | Carry out outreach meetings with hotels on promotion of BATs and BAPs | Lunch allowances 5 pax *4 Days Fuel – 50 lit * 4 Days Refreshments/ water 10 pax *4 days | 1000 100 500 | 20,000 20,000 20,000 |
| 3 | Organizing /Holding High level 3 –Days stakeholder meeting- STEP on 27th Nov. 2010 | Accommodation, air tickets (2 N0.), hiring conference, participants allowances (DSA) |  | 300,000 |
| 4 | DEMO site mapping & reprints ( ecological sites/community livilihoods) | Inventory / Mapping & reprints |  | 100,000 |
| 4 | procurement | 1 No. Office printer (HP)- 4 in one – scanner, printer, photocopier, fax |  | 50,000 |
|  |  | 1 No. High resolution digital camera(marine use) |  | 80,000 |
|  | Proposed activity | Requirements | Unit cost | Total cost (Ksh) |
|  |  | 1 No. Professional Digital video |  | 100,000 |
|  | Procurement | 1 No. Desk top Computer |  | 80,000 |
|  |  | Laptop |  | 100,000 |
|  |  | Office equipments Executive chair, executive Desk, 2 No. office tables 4’x6 ‘, 6 N0. Office chairs, 1 set linked steel visitors chairs, computer desk) |  | 120,000 |
|  |  | Vehicle repair & maintenance |  | 100,000 |
|  |  | Communication- 6 months (air time ) | 3000 | 18000 |
|  |  | GRAND TOTAL |  | 1,188,000 |

PLAN OF ACTION –WATAMU DEMO-SITE, KENYA

| Activity | Activity in the Annual Plan | Concrete Actions | Time Frame (start)- FY: 2010/11 | Budget | Responsibility |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Q 1 | Q2 | Q3 | Q4 | UNIDO | OTHER |  |
|  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | may | Jun |  |  |  |
| Project management | Signing of project MOU | Signing of the project commitment documents Issuance of appointment letter to DEMO Coordinator |  |  |  |  |  |  |  |  |  |  |  |  | - | - | Regional coordinator/Focal point |
|  | Community sensitization & Establishment of DEMO site Management Committee | Holding of 4No. consultative stakeholder meetings for identification of Stakeholders & adoption of DEMO site Committee/work plans Requirements Fuel – 50lit *4days@100/= 5 pax lunches *4Days @1000 Refreshments (Water &teas 20 Pax *4 Days @ 500/=) |  |  |  |  |  |  |  |  |  |  |  |  | 20,000 20,000 40,000 |  | Focal Point/DEMO Coordinator |
|  |  |  | SUB-TOTAL | 80,000/= |  |  |
|  |  | 2.2Holding 2 -level Stakeholder workshops (20 pax per Workshops on project programmes(loframe/M&E) .Best practices/Technology & capacity building, EMS , Labeling/certification/policy /legal reviews/conflict resolution/mechanism for sustainable tourism Requirements (fuel , 5 No. air tickets, DSA, Participation allowance, venue hire, stationery & accommodation) |  |  |  |  |  |  |  |  |  |  |  |  | 600,000/= |  |  |
| Activity | Activity in the Annual Plan | Concrete Actions | Time Frame (start)- FY: 2010/11 | Budget | Responsibility |
|  |  |  | Q 1 | Q2 | Q3 | Q4 | UNIDO | OTHER |  |
|  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | may | Jun |  |  |  |
|  | Public awareness creation, marketing & promotion of best practices, assessment environmental competition& awards | Develop& Design publicity/marketing materials For: Certification, eco-tourism, code of practice, reef protection, turtle protection, beach protection, HIV aids/Gender Requirements Brochures 2000 No. @ 100 /=Printing, T- Shirts 500 No @ 300/=)posters (1000 No@ 200.0 brochures, websites, information desk-centre) |  |  |  |  |  |  |  |  |  |  |  |  | 200,000 150,000 200,000 50,000 |  | ;; |
|  |  |  | SUB-TOTAL | 600,000/= |  |  |
|  |  | 3.2 carry out outreach dissemination programme by use of :- local media , - local artists, -Beach cleanups -public meetings/Baraza (on quarterly Basis – 2 No. Barazas, 2 no cleanups,4 no awareness /assessment campaigns Requirements (Fuel 50lits *8 Days* 3 No Vehicles@100/= groups allowance /refreshments (2 No. cleanups @ 60,000/=) lunch allowances- 5 No officers *8days@1000/= Radio advertisements (4 No @ 5000/=) |  |  |  |  |  |  |  |  |  |  |  |  | 120,000 120,000 40,000 20,000 |  |  |
|  |  |  | SUB-TOTAL | 300,000 |  |  |
| Activity | Activity in the Annual Plan | Concrete Actions | Time Frame (start)- FY: 2010/11 | Budget | Responsibility |
|  |  |  | Q 1 | Q2 | Q3 | Q4 | UNIDO | OTHER |  |
|  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | may | Jun |  |  |  |
|  |  | Mapping the DEMO site , Reefs, livelihood activities & map reprints |  |  |  |  |  |  |  |  |  |  |  |  | 200,000 |  |  |
|  |  |  | SUB_TOTAL |  | 200,000 |  |  |
|  | Capacity building (Purchase of project equipments) & administrative costs | purchase office Printer |  |  |  |  |  |  |  |  |  |  |  |  | 50,000 |  |  |
|  |  | 4.2 Purchase office desk top Computer |  |  |  |  |  |  |  |  |  |  |  |  | 100,000 |  |  |
|  |  | 4.3 office furniture (2 No. Office desks , 6 No. office Chairs, computer desks) |  |  |  |  |  |  |  |  |  |  |  |  | 100,000 |  |  |
|  |  | 4.4 I no digital camera & 1 No. digital video (professional Cam recorder) |  |  |  |  |  |  |  |  |  |  |  |  | 80,000 100,000 |  |  |
|  |  | 4.5 vehicle repair & maintenance (quarterly – 50,000/= |  |  |  |  |  |  |  |  |  |  |  |  | 200,000 |  |  |
|  |  | 4.6 Communications ( stationery @ 22,500 /quarter Internet / airtime 1 pax @4000/= *12 months, 2pax @3000*12mo |  |  |  |  |  |  |  |  |  |  |  |  | 90,000 120,000 |  |  |
|  |  | 4.7 Demo Coordinator allowance 1 pax@40000*12months |  |  |  |  |  |  |  |  |  |  |  |  | 480,000 |  |  |
|  | promotion of best practices & technology | 5.1EFFECTIVE waste disposal systems & conservation proposals for groups funding Environmental awards . community BATs/BAPs |  |  |  |  |  |  |  |  |  |  |  |  | 300,000 |  |  |
|  |  | GRAND TOTAL | 3,260,000 |  |  |