Kenya Demo Project: Watamu (with capacity building linkage to Wasini) – Revised Logical Framework

Overall Goal: Supporting the conservation of globally significant coastal and marine ecosystems and associated biodiversity in sub-Saharan Africa, through the reduction of the negative environmental impacts which they receive as a result of coastal tourism

| Narrative | Objectively Verifiable Indicators (OVI) | Means of Verification (MoV) | Assumptions/Risks |
| --- | --- | --- | --- |
| 1. Main Result 1 (Component 1) Developed and tested BAPs and BATs for reducing land-sourced pollution and degradation resulting from tourism | The number of BAPs and BATs tested and developed namely; one on water recycling and efficiency, one on eco-tourism partnerships and one on EMS, eco-labelling and certification | Project publications and website resources Stakeholder views and perspectives from participatory surveys | BATs and BAPs can be developed and tested with significant results within a 3-4 year time period |
| Activities contributing towards Result 1: |  |  |  |
| Establish a monitoring baseline and process indicators to assess progress during demo project implementation Work with selected hotels to demonstrate an investment rationale for EMS, eco-certification and labelling Identify actions required by hotels and partners in order to obtain Green Key and Blue Flag certification Test and evaluate the uptake of EMS within supply chain relationships Build upon WIO-LAB BAT to demonstrate how improved waste water quality can improve the environment in Watamu town Develop and test a model for reducing stakeholder conflicts and improved benefit sharing mechanisms Develop and test improved marketing for community-based eco-tourism initiatives Support participatory planning and design of investments within the marine park area Identify and map community protected areas and obtain legal recognition of the same | Regular collection, collation and analysis of demo project data Evidence demonstrating the investment rationale based upon real facts and figures from demo hotels and operators involved in the project Evidence in the form of a vision statement and action plan pathway for hoteliers to work towards Evidence of data on EMS supply chain relationship and targets based upon selected demo project hoteliers Physical development of a demo waste water facility Baseline and follow up monitoring environmental data Evidence of a practical conflict management mechanism being used The number and type of community-based initiatives being marketed through local hoteliers and operators compared with the baseline year Evidence of diverse stakeholder involvement in KWS marine park planning mechanisms KWS recognition of the value of such sites Agreed process for legal recognition in place | Project publications and website resources Stakeholder views and perspectives from participatory surveys Consultancy reports |  |
| 2. Main Result 2 (Component 2) Developed mechanisms for sustainable tourism governance and management | A coastal zone task force or committee with diverse representation of stakeholders is meeting on a regular and effective basis, and is able to influence government and private sector initiatives within the same zone | Project reports Coastal zone committee meetings and reports Stakeholder views and perspectives from participatory surveys | The existing CZM committee will welcome the COAST project and be willing to take on and promote the recommendations arising from the demo sites, thereby providing a mechanism for influencing governance and future policy |
| Activities contributing towards Result 2: |  |  |  |
| 2.1 Test and evaluate the draft Tourism policy within the demo project area, and provide feedback to the CZM committee 2.2 Review the Tourism planning mechanisms and provide feedback to the CZM committee 2.3 Monitor, review and provide recommendations on the pricing policy and benefit sharing mechanisms within the marine national parks 2.4 Develop a disaster preparedness plan which is integrated across all relevant sectors 2.5 Provide advice and support to enhance the environmental award scheme for hotels, community groups and schools 2.6 Review current EIA and auditing processes within NEMA and modify so as to make specific to the tourism sector 2.7 Review standards, policies, and regulations on infrastructure planning and development in line with the draft tourism policy 2.8 Develop a coordination model for sustainable tourism at Watamu as an example of destination planning 2.9 Commission a consultancy to examine options for sustainable financing approaches for community tourism 2.10 Develop and test a code of conduct for reef users 2.11 Review zoning, use and boat operator rules and regulations | Evidence of the feedback and results provided to the CZM committee and evidence of policy revisions Evidence of feedback on the mechanisms and the debates and decisions made as a result by the CZM committee Changes in pricing and benefit sharing mechanisms and policy within KWS The existence of a disaster preparedness plan and awareness and clarity on the various roles across the relevant stakeholders Increased community and private sector interest in the awards. Increased sponsorship Evidence of modification of the NEMA EIA process in relation to the tourism sector Number of recommendations on changes in policy, regulation and standards made, and the number approved within the draft policy Evidence of a sustainable coordination mechanism for destination planning at the demo site Completed consultancy and its recommendations Existence of the code of conduct and the number of operators and hotels promoting its use Changes in the use zoning and operator rules and regulations as a direct result of project activity | Project publications and website resources Stakeholder views and perspectives from participatory surveys |  |
| 3. Main Result 3 (Component 3) Delivered training and capacity building in sustainable tourism using an integrated approach | Evidence of consistency between the training needs assessment and training design and delivery Evidence of locally available training courses on the topics originally designed and promoted by the demo project | Project publications and website resources Stakeholder views and perspectives from participatory surveys | Suitable locally based research, education or training organisation is interested to partner with the project to develop local stakeholder capacity in sustainable tourism management |
| Activities contributing towards Result 3: |  |  |  |
| 3.1 Identify and establish an MoU with a locally based training and/or research institute in order to build sustainable tourism management capacity along the Kenya coast 3.2 Design and deliver EMS training for selected hotels in the demo site area 3.3 Commission a consultancy to undertake a training needs assessment for stakeholder and community level training and design and deliver training in one or more of the following (water sports, languages, sustainable fishing, business planning, tourism management) 3.4 Design and deliver reef ecology, recreation and conservation management training | Nature and effectiveness of the MoU as measured by the number and diversity of trainings held Number and type of hotels and tour operators who have benefited Training needs assessment report and the number of trainings design and delivered during the demo project period Number of stakeholders benefiting from the training and changes in visitor practice and/or management of the reef areas within the demo site | Project publications and website resources Stakeholder views and perspectives from participatory surveys Consultancy reports |  |
| 4. Main Result 4 (Component 4) Captured, managed and disseminated information to assist in replication and uptake of best practices and lessons | Number and type of the BAPs and BATs documented and disseminated Number and type of media used to disseminate the project results | Project publications and website resources Stakeholder views and perspectives from participatory surveys | Stakeholders within the demo project area are willing to share their experiences with other areas and organisations beyond the demo project site |
| Activities contributing towards Result 4: |  |  |  |
| 4.1 Extend the existing sensitivity mapping using GIS to cover tourism use and local livelihood use for both marine and land-based activities 4.2 Develop and test an enhanced monitoring mechanism for destination planning using UNWTO indicators and experiences 4.3 Design and disseminate HIV/AIDS and gender awareness materials widely within the demo project area in order to address equity concerns among stakeholders 4.4 Design and deliver information on reef conservation and management activities to tourists and hotels 4.5 Map reef areas, and marine use and link with existing KEMFRI data 4.6 Market reef and turtle monitoring and conservation work as a tourist experience within the demo site area | Number, type and use of maps produced and uptake by stakeholders Monitoring data and results of analysis exist Number and type of materials produced and the extent of their dissemination Number and type of information materials produced and the extent of their dissemination Number, type and use of the maps produced and uptake by stakeholders Availability of such information in hotels and tour operator offices, and their visitor packages | Project publications and website resources Stakeholder views and perspectives from participatory surveys |  |