REPÚBLIC OF MOÇAMBIQUE

MINISTERY FOR COORDINATION OF ENVIRONMENTAL -MICOA

PROVINCIAL DIRECTORAT FOR COORDINATION OF ENVIRONMENTAL-INHAMBANE

COAST- PROJECT

WORK PLAN FOR PROJECT DEMO SITE – MOZAMBIQUE (2nd YEAR-2011)

| ACTIVITIY OF GLOBAL PLAN | ANNUAL PLAN | ACTION | TIME | BUDGET | RESPONSIBLE |
| --- | --- | --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | UNIDO | other |  |
| 1.Project Management | 1. Develop and agree an MoU and sub contract between UNIDO and MICOA incorporating support from; Tourism Ministry (MITUR) | MoU and Sub contract between UNIDO and MICOA agreed |  |  |  |  |  |  |  |  |  |  |  |  | --------- |  | UNIDO and MICOA |
|  | 2.Agree disbursement procedure for demo project GEF funds | Disbursement procedures agreed |  |  |  |  |  |  |  |  |  |  |  |  | --------- |  | UNIDO and MICOA |
|  | 3. Recruit Demo Project Coordinator | Demo Project Coordinator recruited |  |  |  |  |  |  |  |  |  |  |  |  | $ 5. 500 |  | UNIDO and MICOA/DPCAAI |
|  | 4. Purchase a motor bike an office room with computer, printer, internet link and for Demo Coordinator | Office room and equipment operational |  |  |  |  |  |  |  |  |  |  |  |  | $5. 000 |  | Focal Point, Project Demo Site Coordinator, and MICOA/DPCAAI |
|  | 5. Prepare and implement initial demo project awareness raising activities (public event, brochure) | 1.5.1 Involve local partners and stakeholders aware of new demo Project and activities |  |  |  |  |  |  |  |  |  |  |  |  | $ 1. 390 |  | Focal Point and Project Demo Site Coordinators DPCAAI |
|  |  | 1.5.2 Identify and nominate key representatives from each stakeholder group as a local management committee) |  |  |  |  |  |  |  |  |  |  |  |  | $ 500 |  | Project Demo Site Coordinator, DPCAA/DPTUR |
|  |  | 1.5.3Preparation of brochures to introduce project activities(3 seminary) |  |  |  |  |  |  |  |  |  |  |  |  | $ 1.111 |  | Project Demo Site Coordinator and local specialist |
| 2. Development and Test BATs and BAPs for reducing land sourced pollution and degradation and environment. | 6. Undertake a local assessment of capacity gaps and training needs vis-à-vis the proposed BATs and BAPs & report the results | Undertake training needs analysis |  |  |  |  |  |  |  |  |  |  |  |  | $ 0,0 |  | Consultants |
|  | 7.Undertake a baseline survey to identify the key sources of local land-based contamination, erosion, biodiversity / environment / social stress at the demo project area and report the results | 2.7.1Identify a Consultant/team of experts and develop TOR for research pollution causes and report the results |  |  |  |  |  |  |  |  |  |  |  |  | $ 2.500 (ICZM, consultants) $ |  | Project Demo Site Coordinator and Consultants/ team of experts |
|  |  | 2.7.2Provide coordination for baseline monitoring and data collection exercise and supervise the analysis & reporting of the same |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Demo Site Coordinator and local stakeholders |
|  |  | 2.1 Develop a partnership action plan/pathway for each activity and agree roles |  |  |  |  |  |  |  |  |  |  |  |  | $500 |  | Project Demo Site Coordinator and Consultants/ team of experts |
|  |  | 2.1Design and agree an information collection, analysis, use and dissemination action plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Demo Site Coordinator and local stakeholders |
|  |  | 2.3 Identify and establish and MoU/LOA with Tourism College or research institute for training delivery. |  |  |  |  |  |  |  |  |  |  |  |  | $ 600 |  | Project Demo Site Coordinator and a team of experts |
| 3.Developed mechanism for sustainable tourism governance and management | 8. Begin work in Tofo to produce a coastal zone use plan & map for sustainable destination planning | Identify a Consultant or team of experts to Produce and disseminated coastal zone use plan & map |  |  |  |  |  |  |  |  |  |  |  |  | $ 15.000 + $ 2.500 (GIS Consultants) $ 3000 (EMS Consultants) |  | demo Coordinator, (Environment & Tourism department) and a team of experts |
|  | 9. Begin work in Pomene to plan for a short (2-3 months) technical input to work with local stakeholders to produce a coastal zone use & conservation plan & map critical areas. | Identify an Consultant or team of experts and develop TOR for produce a coastal zone use plan and map. |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Coordinator, Focal points (Environment & Tourism department) and a team of experts |
|  | 10. Design and produce educational materials on HIV/AIDS, gender and and disseminate throughout the project period | Produce educational materials on HIV/AIDS, gender environmental conservation and disseminate |  |  |  |  |  |  |  |  |  |  |  |  | $ 1000 |  | Project Coordinator, Focal points (Environment & Tourism department) and a team of experts |
| Project Management activities | 11.Meetings with local management committee | Develop meetings for evaluation progress activities and prepare a work plan for the year 2010/2011. |  |  |  |  |  |  |  |  |  |  |  |  | $ 2000 |  | Project Coordinator, Focal points |
|  | 12.Translations and web information | Translations and send information |  |  |  |  |  |  |  |  |  |  |  |  | $ 2.000 |  | Project Coordinator, Focal points, DPCAAI |
|  | 13.Participatory M&E annual assessment exercise | Meetings with local management committee, Advisor group, focal point |  |  |  |  |  |  |  |  |  |  |  |  | $ 1.750 |  | Project Coordinator, Focal points, DPCAAI |
|  | Communications postage and small supplies | Coordinate activities |  |  |  |  |  |  |  |  |  |  |  |  | $ 300 (available from UNIDO country office) |  | Project Coordinator, Focal points, and DPCAAI |
| Total |  | $ 44. 351 |  |  |

The original budget line from Equipment and Premises is  $ 6000, so was subtracted $1000 to activity nº (10) and 1600 was subtracted from Pro bono Management Committee meetings to activities (1.5.2, 2.1 and 2.3)

Mozambique, 05 December 2010