REPÚBLIC OF MOÇAMBIQUE

MINISTERY FOR COORDINATION OF ENVIRONMENTAL -MICOA

PROVINCIAL DIRECTORAT FOR COORDINATION OF ENVIRONMENTAL-INHAMBANE

COAST- PROJECT

PROGRESS Expenditure FOR PROJECT DEMO SITE – MOZAMBIQUE (October- 2010 January 2011)

COAST Project Expenditure :

Project Period: From Octuber-2010 To January2011

Project no: GP/RAF/08/004	Agency Name: Ministry of Environment MOZ.

## Project Title: “Community based in eco-tourism, reef management and environmental management systems, focusing on Tofo Bay and Pomene Reserve and coastline”.

Project Commencing: January 2010		Project Ending: December 2013

< COAST Sub contract Ref: Moz1/10 with UNIDO and MICOA September 2010>

| Object of expenditure by budget Code | Project budget allocation for year 2010/11 |  | Total expenditure for period | Total un-liquidated obligations* | Cumulative expenditure for period | Unspent balance for budget allocation for the period |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | m/m (1) | Amount (2) | (3) | (4) | (5) | m/m (6) | Amount (2-5) |
| Project Personnel Component (Demo Project Coordinator) |  | $ 5.500,00 | 500,00 | 5.000,00 | 5.500,00 | 0 |  |
| Miscellaneous Component (Brochures, publicity information, communications and small supplies) |  | $ 5.711,00 | 2.300,00 | 0 | 2.300,00 | 3.411,00 |  |
| Training component (Stakeholder awareness meetings and management Committee meetings) |  | $ 5.267,00 | $1.950,00 | 0 | 1.950,00 | 3.317,00 |  |
| Sub-Contract Component ( mapping Activities, production of Land Use Plan in Tofo⁄Pomene and Undertake a baseline of local land-based contamination, erosion, biodiversity and social stress) |  | $ 15.000,00 + 7500,00 Consultant | 750,00 | 9.250,00 | 10.000,00 | 5.000,00 + 7.500,00 |  |
| Equipment And Premises LapTop and Printer |  | 6.000 | 0 | 2.000 | 2.000,00 | 4.000,00 |  |
| Grand Total |  | 44.978,00 | 5.500,00 | 16.250,00 | 21.750,00 | 23.228,00 |  |

Signed:

---------------------------------------------------------------------

Authorized official of Executing Agency

Notes on funds committed but not yet spent:

The First Total Budget made available for the first Period was 396, 312,00 MT = USD 11.243,2

- Reference Project Personnel Component budget to be paid when the money be available.

- Reference Sub-Contract Component, $ 9250,00 is to be paid to local experts and consultant once they start the activities50% and submits the final report50%.

- Reference Equipment budget $2000 is to be paid upon receipt of the ordered laptop computer.