Nigeria Demo Project (1) Badagry: – Revised Logical Framework

Overall Objective: To promote improved conservation, management and monitoring of the coastal & lagoon biodiversity, and to enhance and diversify the tourism experience and local livelihoods through eco-tourism as a means of alleviating poverty.

| Narrative | Objectively Verifiable Indicators (OVI) | Means of Verification (MoV) | Assumptions/Risks |
| --- | --- | --- | --- |
| 1. Main Result 1 (Component 1) Developed and tested BAPs and BATs for reducing land-sourced pollution and environmental degradation resulting from tourism | The number of BAPs and BATs tested and developed namely; one on waste management mechanisms, one on eco-tourism partnerships and one on historical/heritage tourism and protection | Project publications and website resources Stakeholder views and perspectives from participatory surveys | BATs and BAPs can be developed and tested with significant results within a 3-4 year time period |
| Activities contributing towards Result 1: |  |  |  |
| 1.1 Develop baseline environmental, social and economic indicators for the site 1.2 Review and promote the rights of indigenous peoples by identifying community aspirations (through community visioning exercises) particularly regarding ecotourism & heritage tourism developments in the peninsular area Support the development of information/ interpretation centres at each heritage site along the ‘heritage pathway’, in addition to other facilities as appropriate through PPPs (toilets, restaurant and retail facilities) Produce and disseminate a code of conduct (for Badagry peninsular and lagoon) incorporating cultural and social themes, environmental management, and development best practices. Develop a toolkits (steps) for local stakeholders on how to develop public-private partnerships; establish CBEs; and broker joint-venture partnership agreements 1.6 Support the development and publicity of a local tourism calendar of events for Badagry peninsular and lagoon area Provide technical assistance and support, for a comprehensive tourism development and land use plan for the Badagry peninsular and lagoon area as a contribution to the overall eco-tourism Masterplan (2008) Develop environmentally appropriate waste and sewage disposal infrastructure plan for all heritage sites to protect the wetlands and natural beauty of the area and ensure hygienic working conditions | Regular collection, collation and analysis of demo project data Evidence in the form of a vision statement and action plan pathway for communities to work towards The number and type of community-based initiatives being marketed through local hoteliers and operators compared with the baseline year Number and use of interpretation centres and associated facilities Number of visitors to ‘heritage pathway’ Awareness of key eco-tourism issues among tourists and local community members Number of copies dispatched to; investors, tourists and local community members Evidence of a documented toolkit Number of joint-venture partnerships signed or in process of development Number of events organised during each year, publicity about the events and the number of CBEs with stalls and number of attendees /visitors from different organisations Completion and dissemination of the plan and associated maps. Acceptance of the peninsular plan by State and local authorities Changes in waste and sewage disposal methods/infrastructure as compared with baseline year | Project publications and website resources Draft data and eco-tourism masterplan document 2008 Stakeholder views and perspectives from participatory surveys Consultancy reports Stakeholder views and perspectives from participatory surveys | Interest from private and public sector bodies to work in joint venture developments with the identified communities (including local banks) Local banks will be interested to partner and finance such developments |
| 2. Main Result 2 (Component 2) Developed mechanisms for sustainable tourism governance and management in Badagry | A coastal zone task force or multi-partner group with diverse representation of stakeholders is meeting on a regular and effective basis, and is able to influence local and State government and private sector initiatives within the same peninsular zone | Project reports Coastal zone multi-partner meetings and reports Stakeholder views and perspectives from participatory surveys | The existing stakeholders will welcome the COAST project and be willing to take on and promote the recommendations arising from the demo sites, thereby providing a mechanism for influencing governance and future policy. The draft eco-tourism masterplan will be adopted by the Lagos State Government during the project period thus underpinning our Badagry initiatives |
| Activities contributing towards Result 2: |  |  |  |
| 2.1 Support the development of a multi-partner stakeholder group, including government departments of environment, tourism, marine resources, community based organisations, NGOs, private investors, to improve communication & cooperation, reduce overlapping mandates and resolve conflicts within the coastal tourism sector 2.2 Specifically support and test the implementation of a set of Responsible Tourism Guidelines, including EIA criteria, for Nigeria (Lagos State), within the framework of the Eco-tourism Masterplan, (drafted 2008) 2.3 Clarify institutional mechanisms incorporating coordination and cooperation between stakeholders at local, State levels to support smooth implementation of the Eco-tourism Masterplan in the Badagry area 2.4 Develop steps and then raise public and investor awareness regarding these (key steps for successful design & investment) and enforce them 2.5 Introduce an entry fee for visitors to the ‘heritage pathway experience’ to raise revenue for heritage conservation and community art & craft training & development | Evidence of the feedback and results provided to the multi-partner group and evidence of policy revisions Evidence of a sustainable coordination mechanism for destination planning at the demo sites Number of recommendations on changes in policy, regulation and standards made, and the number approved Use of these guidelines and framework with demo project area Clarified linkages and mandates documented and being utilised for new investments The number of disseminated materials to public and private investors within the Badagry area and the number of investors following the regulations Documented outcome from entry /user fee assessments. Amount of revenue raised and re-invested | Project publications and website resources Meeting reports and recommendations Stakeholder views and perspectives from participatory surveys Partner organisation reports Eco-tourism Masterplan document and Responsible Tourism Guidelines |  |
| 3. Main Result 3 (Component 3) Delivered training and capacity building in sustainable eco- and heritage tourism using an integrated approach | Evidence of consistency between the training needs assessment and training design and delivery Evidence of locally available training courses on the topics originally designed and promoted by the demo project | Project publications and website resources Stakeholder views and perspectives from participatory surveys | Suitable locally based research, education or training organisation is interested to partner with the project to develop local stakeholder capacity in sustainable eco-tourism management |
| Activities contributing towards Result 3: |  |  |  |
| 3.1 Identify and establish an MoU with a locally based training and/or research institute in order to build sustainable eco-tourism management capacity within Lagos State, Nigeria 3.2 Commission a consultancy to undertake a training needs assessment for stakeholder and community level training and design and deliver training 3.3 Training support for Badagry guides in the area of eco- and heritage tourism 3.4 Support exchange visits between Nigerian and other regional eco-tourism initiatives for capacity building purposes | Nature and effectiveness of the MoU as measured by the number and diversity of trainings held Training needs assessment report and the number of trainings design and delivered during the demo project period Number and type of individuals and community associations who have benefited Number of stakeholders benefiting from the training and exchange visits. Changes in management practices resulting from such visits at demo sites | Project publications and website resources Stakeholder views and perspectives from participatory surveys Partner organisation reports Consultancy reports Visit reports |  |
| 4. Main Result 4 (Component 4) Captured, managed and disseminated information to assist in replication and uptake of best practices and lessons | Number and type of the BAPs and BATs documented and disseminated Number and type of media used to disseminate the project results | Project publications and website resources Stakeholder views and perspectives from participatory surveys | Stakeholders within the demo project area are willing to share their experiences with other areas and organisations beyond the demo project site |
| Activities contributing towards Result 4: |  |  |  |
| 4.1 Targeted awareness raising to encourage enforcement of natural resource sustainable use, improved waste management, improved heritage management and eco-tourism partnerships within the Badagry peninsular and lagoon area 4.2 Design and disseminate HIV/AIDS and gender awareness materials widely within the demo project area in order to address equity and public health concerns among stakeholders 4.3 Promote and support the development of an annual calendar of events for tourism in the Badagry area 4.4 Disseminate lessons of best practice and advances in Nigerian eco- and heritage-tourism through case studies that include tangible information on socio-economic and environmental improvements | Number, type and extent of awareness raising events Number and type of materials produced and the extent of their dissemination Number and type of information materials produced and the extent of their dissemination Availability of such information in Local, State, Federal Government agencies, hotels and tour operator offices, and in their visitor packages and websites | Project publications and website resources Stakeholder views and perspectives from participatory surveys |  |