UNITED REPUBLIC OF TANZANIA

THE VICE PRESIDENTS OFFICE

COAST- PROJECT

DRAFT WORK PLAN FOR PROJECT DEMO SITES –YEAR-2011/2012

| ACTIVITY OF GLOBAL PLAN | ANNUAL PLAN | ACTION | TIME | BUDGET | RESPONSIBLE |
| --- | --- | --- | --- | --- | --- |
| 1. Project Management | 1.1 Agreement and signing of the contract for second disbursement of funds | 1.1.1 Agree and signing Sub contract between UNIDO and VPO-DoE | JANUARY |  | VPO-DoE UNIDO |
|  |  | 1.1.2 Identify training/ research institute and establish MoU for training delivery | FEBRUARY |  | Demo coordinator, Environment and Tourism focal Point |
|  |  | 1.1.2 Stipend for the Demo coordinator | JAN - DEC | $6000 | Demo coordinator, Environment and Tourism focal Point |
|  | 1.2 Conduct Tourism Value Chain Analysis | 1.2.1 Conduct Tourism Value Chain Analysis of one demosite(Bagamoyo) | MARCH | $3000 | UNIDO Demo coordinator, Environment and Tourism focal Point |
|  | 1.3 Conduct Tourism Policy and Governance Study | 1.3.1I dentify Local consultant to work with the Lead consultant | MAY | $4000 | Consultants, UNIDO-RCU |
|  | 1.4 Meetings with local management committee | 1.4.1Develop meetings for evaluation progress activities and prepare a work plan for the year 2012/2013. 1.4.2 Participatory M&E and annual assessment exercise 1.4.2 Meetings with local management committee, Advisor group, focal point Coordinate activities | MARCH JUNE SEPT DEC | $8000 | Demo coordinator, Environment and Tourism focal Point |
|  | 1.7 Communications postage and small supplies | 1.7.1Communication with stakeholders and Demosite management comitees | JAN - DEC | $500 | Demo coordinator |
| 2. Establishment and Implementation of Environmental Management Systems and Voluntary Eco-certification and Labeling Schemes | 2.1 To increase capacity of Tourism stakeholders to Initiate and ImplementEMS and Eco-certification | 2.1.1 Conduct specialized EMS training through a training of trainers (TOT) | MARCH | 30,000 | UNIDO |
|  |  | 2.1.2 Identify hotels that are willing to start implementing EMS and Eco-certification | MARCH |  | Demo coordinator, Environment and Tourism focal Point |
|  |  | 2.1.3 Conduct EMS training in local hotels | MARCH-DEC |  |  |
| 3. Developed mechanism for Capacity building and awareness on coral reef management | 3.1 Produce a coastal zone use plan for sustainable destination planning that help to minimize impacts on coral reefs | 3.1.1 To conduct conservation education programmes to tour operators and fishermen reef | MARCH - DEC | $5000 | Demo coordinator, Environment and Tourism focal Point |
|  |  | 3.1.2 Agree on code of conduct for reef users through participatory process. | MARCH-MAY | $2000 | Demo coordinator, Environment and Tourism focal Point, demosite stakeholders |
|  |  | 3.1.3 Boat operators and snorkel/dive guides encouraged to regulate and ensure their implementation. | MARCH - DEC |  | Demo coordinator, Environment and Tourism focal Point, demosite stakeholders |
|  |  | 3.1.4 To conduct community based and local stakeholder reef monitoring programmes that involve tour operators and fishermen | MARCH - DEC | $10,000 | Demo coordinator, Environment and Tourism focal Point, demosite stake holders |
| 4. Eco-tourism initiatives for the communities around the demo sites | 4.1 Beginning to work on alternative livelihoods, poverty alleviation and revenue generation for conservation | 4.1.1 Identify a consultant or expert to develop and implement a tourism product development and marketing strategy for community based tourism an tourism activities | MARCH | $2000 | Demo coordinator, Environment and Tourism focal Poin and Expart. |
|  |  | 4.1.2 Deliver training and education on tourism management, business planning, and marketing strategies. | MARCH - DEC | $30,000 | Demo coordinator, Environment and Tourism focal Point, Trainer |
|  |  | 4.1.2 Review purchasing practices of hotels to increase the share of locally sourced products and services | MARCH - MAY |  | Demo coordinator, Environment and Tourism focal Point, Exparts |
|  | 4.2 Small grants for Commuty based initiatives for poverty alleviation | 4.2.1 I dentifying various community initiatives in the demosites for poverty alleviation | MARCH | 3,000 | Demo coordinator, Environment and Tourism focal Point, Expart |
|  |  | 4.2.2 Assessing and scrutinizing the community based initiatives to be supported by the project | JUNE - JULY | $5000 | Demo coordinator, Environment and Tourism focal Point |
|  |  | 4.2.3 Funding the selected community based initiatiatives | JULY | $50,000 | Demo coordinator, Environment and Tourism focal Point, Exparts |
|  |  | 4.2.4 Mornitoring the performance of the activities supported by the project | JILY - DEC | $3000 | Demo coordinator, Environment and Tourism focal Point, Exparts |