Tanzania Demo Project:   – Revised Logical Framework

Overall Objective: Integrated Sustainable Tourism Destination Planning with a specific focus on eco-labelling, eco-certification and eco-tourism on Mafia Island. Environmental Management Systems and Eco-tourism in Kinondoni, and Eco-tourism and Environmental Management Systems in Bagamoyo.

| Narrative | Objectively Verifiable Indicators (OVI) | Means of Verification (MoV) | Assumptions/Risks |
| --- | --- | --- | --- |
| 1. Main Result 1 (Component 1) Developed and tested BAPs and BATs for reducing land-sourced pollution and degradation, and environmental and social stresses resulting from tourism | The number of BAPs and BATs tested and developed namely; on water recycling and efficiency, on eco-tourism partnerships, on EMS, and eco-labelling and certification | Project publications and website resources Stakeholder views and perspectives from participatory surveys | BATs and BAPs can be developed and tested with significant results within a 3-4 year time period |
| Activities contributing towards Result 1: |  |  |  |
| Establish a monitoring baseline and process indicators at each demo site to assess progress during demo project implementation Work with selected hotels in the Chole Bay area on Mafia Island to develop an eco-certification and eco-labelling plan and provide TA to begin implementation Work with DED and hotels in the Bagamoyo bay area to reduce environmental stress through improved solid waste management (plastics and other wastes) Test and evaluate the uptake of EMS within hotels established along the Kinondoni beaches with particular reference to water recycling and re-use Work with WASCOS members on Mafia Island to improve their marketing and expand their ‘niche’ eco-tourism portfolio Work with one of the mainland mangrove eco-tourism community groups (either Mbudya or Mbweni) to market and strengthen their tourism products and reduce environmental degradation | Regular collection, collation and analysis of demo project data Evidence demonstrating the investment rationale based upon real facts and figures from demo hotels and operators involved in the project Evidence in the form of an action plan pathway for hoteliers to work with the local council and progress against markers along this Case study evidence from the Golden Tulip hotel being used by other hoteliers to invest in improved water management facilities as part of an EMS approach Physical development of a demo waste water facility Baseline and follow up monitoring environmental data The number and type of community-based initiatives being marketed through local hoteliers and operators compared with the baseline year | Project publications and website resources Stakeholder views and perspectives from participatory surveys Consultancy reports | Willingness of private hoteliers and investors to fund developments in technology and management processes that are an integral part of the eco-certification process |
| 2. Main Result 2 (Component 2) Developed mechanisms for sustainable tourism governance and management | A coastal zone task force or eco-tourism task force with diverse representation of stakeholders is meeting on a regular and effective basis, and is able to influence government and private sector initiatives within the same zone | Project reports Coastal zone committee meetings and reports Stakeholder views and perspectives from participatory surveys | Government interest to establish an eco-tourism taskforce is realised and the COAST project is able to promote the recommendations arising from the demo sites through this, thereby providing a mechanism for influencing governance and future policy |
| Activities contributing towards Result 2: |  |  |  |
| 2.1 Assess implementation impacts of the EMA (2005) and associated regulations (9) within the tourism sector and make recommendations for improvement 2.2 Ensure that feedback and results from the demo sites is also made available to the Zanzibar government 2.3 Support DED in progressing the draft eco-tourism strategy for Bagamoyo 2.4 Feed demonstration results into the National Strategy for Urgent Action on Coastal Environments 2.5 Commission a consultancy to examine options for sustainable financing approaches for community tourism and eco-tourism | Evidence of the feedback and results provided to the taskforce/ committee and evidence of policy and/or regulatory revisions Evidence of joint sharing meetings and exchange visits Eco-tourism strategy finalised and being implemented Evidence of modification of the strategy development and process of implementation in the tourism sector as a result of demo project activities Completed consultancy and its recommendations | Project publications and website resources Stakeholder views and perspectives from participatory surveys Project reports Partner reports Consultant reports |  |
| 3. Main Result 3 (Component 3) Delivered training and capacity building in sustainable tourism using an integrated approach | Evidence of consistency between the training needs assessment and training design and delivery Evidence of locally available training courses on the topics originally designed and promoted by the demo project | Project publications and website resources Stakeholder views and perspectives from participatory surveys | Suitable locally based research, education or training organisation is interested to partner with the project to develop local stakeholder capacity in sustainable tourism management |
| Activities contributing towards Result 3: |  |  |  |
| 3.1 Identify and establish an MoU with a locally based training and/or research institute in order to build sustainable tourism management capacity along the Tanzanian coast and island communities 3.2 Commission a consultancy to undertake a training needs assessment for stakeholder and community level training and design and deliver training in one or more of the following (EMS, eco-labelling, eco- tourism , waste management, business marketing & management) 3.3 Design and deliver Eco-labelling and eco-certification training for selected hotels on Mafia island 3.4 Work with BATREN and the Bagamoyo cultural tourism and training community organisation to build capacity & design and deliver locally relevant training (e.g. reef ecology, recreation and conservation management) | Nature and effectiveness of the MoU as measured by the number and diversity of trainings held Training needs assessment report and the number of trainings designed and delivered during the demo project period Number of stakeholders benefiting from the training and changes in visitor practice and/or management of the beach & reef areas within Chole Bay Number of stakeholders benefiting from the training and changes in visitor practice and/or management of the beach & reef areas within Bagamoyo area | Project publications and website resources Stakeholder views and perspectives from participatory surveys Project reports Consultancy reports |  |
| 4. Main Result 4 (Component 4) Captured, managed and disseminated information to assist in replication and uptake of best practices and lessons | Number and type of the BAPs and BATs documented and disseminated Number and type of media used to disseminate the project results | Project publications and website resources Stakeholder views and perspectives from participatory surveys | Stakeholders within the demo project area are willing to share their experiences with other areas and organisations beyond the demo project site |
| Activities contributing towards Result 4: |  |  |  |
| 4.1 Develop the existing zonation and mapping base in Mafia island (using GIS) to cover tourism and local livelihood uses for both marine and land-based activities with the objective of enhancing both conservation work and eco-tourism services 4.2 Develop and test an enhanced monitoring mechanism for destination planning building on baseline information, UNWTO indicators and experiences 4.3 Design and disseminate HIV/AIDS and gender awareness materials widely within the demo project area in order to address equity concerns among stakeholders 4.4 Design and deliver information on demo project activities to tourist hotels and outlets 4.6 Coordinate and share information with other ICZM initiatives (e.g. USAID ICZM, MACEMP (WB)) for awareness raising purposes and policy influence | Number, type and use of maps produced and uptake by stakeholders, marketing agents and visitors Monitoring data and results of analysis exist Number and type of materials produced and the extent of their dissemination Number and type of information materials produced and the extent of their dissemination Availability of COAST demo project information and lessons and BAPS/BATs among government officials and among private investors | Project publications and website resources Stakeholder views and perspectives from participatory surveys Project reports Consultant reports |  |