  - COAST Project Revised Logical Framework

| Project objective and Outcomes | Description of indicator | Baseline level | Mid-term target | End-of-project target |
| --- | --- | --- | --- | --- |
| Objective 1 BAPs/BATs strategies for sustainable tourism demonstrated | 1.Mechanisms for reduced degradation understood, in place and being utilised | Baseline information unavailable, but to be confirmed during year 1 of demo implementation, and to include both regional and national level monitoring requirements | All stakeholders and partners aware and understand the major causes of environmental degradation | At least two demo projects have developed mechanisms and are actively testing these to address issues of environmental degradation |
|  | 2. National indicators to demonstrate sustainable improvements have been agreed & are being used (national (including demo project indicators)) | Baseline information unavailable, but to be confirmed during year 1 of demo implementation | National indicators have been agreed with all partner countries and data are beginning to be collected | Five partner countries are using national indicators to monitor and measure improvements |
|  | 3. Project demonstrations providing replicable BATs/BAPs (with costs & benefits) | No baseline information available. | Four demonstrations are actively being implemented employing BAPs/BATs and are in the process of being documented for sharing and knowledge management | All demonstrations are actively being implemented and each has provided at least one BAT/BAP based upon the project’s thematic priorities (EMS, eco-tourism, reefs, ecosystem planning) which has been documented for sharing and knowledge management |
|  | 4. Incentives for sustainable partnerships for civil society, private and public sector documented & disseminated | Baseline information unavailable, but to be confirmed during year 1 of demo implementation | At least one case study for sustainable partnerships documented and disseminated | At least one case study per thematic area (EMS, Reefs, Eco-tourism, ecosystem planning) for sustainable partnerships documented and disseminated |
| Objective 2 Mechanisms for sustainable tourism governance and management established | 1. Project experiences on sustainable tourism documented and disseminated as a contribution to policy debates in all 9 countries | Baseline information available as part of the demo project narratives, but require to be updated during year 1 of demo implementation | Experience sharing for enhancing policy debates underway in at least four countries | Project experiences documented and disseminated as a contribution to policy debates in all partner countries |
|  | 2. Project experiences supporting the development or revision of national strategies and work plans for sustainable tourism | Baseline information unavailable, but to be collected during year 1 of demo implementation as part of a ‘gaps, needs and options’ consultancy | Identification of priority issues for inclusion in National strategies are underway | Project experiences documented and at least one information brief per country disseminated as a contribution towards national strategy development and revision |
| Objective 3 Training and Capacity Building for sustainable tourism delivered | 1. Assessment of training needs for each partner country completed by second SCM | Not existing | Regional assessments completed (East and West Africa) | Regional assessments completed (East and West Africa) |
|  | 2.Training packages dev and implemented to suit national & regional needs | Not existing | Relevant training packages/inputs are being designed and implemented in some partner countries | All partner countries have benefited from at least two thematic training packages developed to suit specific demo project requirements |
|  | 3. Training materials incorporating BATs/BAPs from Objective 1 available by end of Yr 3 | Not existing | Training materials are under development with some content coming from COAST demo project BAPs/BATs | Training materials incorporating COAST BATs/BAPs and other experiences are available to all partner countries and are being used in at least five |
| Objective 4 Establishment of a virtual information coordination & clearing house (eRICH) | 1. eRICH established and fully operational within first 2 yrs | Not existing | eRICH is in place | All partner countries are contributing to eRICH through BAPs/BATs and other project documented experiences |
|  | 2. Project contributing to wider public understanding and sharing of BAPs/BATs through eRICH as measured by the level of use and uptake on the eRICH pages of the COAST website | Not existing | Work with relevant National Environment & Tourism agencies is on-going with the collection of environmental & tourism management information to feed into eRICH | All countries are providing environmental and tourism management information for sharing and dissemination through eRICH |
|  | 3. Lessons from awareness of coastal environment and sustainable tourism principles & practices at demo sites presented on eRICH | Not existing | At least two partner countries have shared early lessons from awareness on the subject matter on eRICH | All countries are providing awareness lessons on the subject matter for sharing and dissemination through eRICH |
| Outcome 1: Working Environmental Management Systems (EMS) in place at appropriate demo sites | 1 National institutes strengthened through EMS training | Not existing | National institutes have initiated demo projects employing EMS at four of the relevant demo project sites | National institutes have monitored & evaluated EMS demo activities in order to share outcomes on; economic, social and environmental benefits |
|  | 2 Increase in capacity of tourism stakeholders to initiate EMS (with the aim to replicate good practices) | Not existing | Stakeholders who are prepared to make their own investments in EMS identified | Collaborative EMS training events involving both domestic and international tour operators have been held in at least two demo sites and have resulted in changes to hotel management practices |
|  | 3 Project experiences in EMS inform policy and regulatory debates | Not existing | Data from Project EMS experiences being collected and collated | Project EMS experiences being documented and disseminated to enhance policy and regulatory debates in at least two partner countries |
|  | 4 Eco-labelling plan and certification schemes operational | Baseline information unavailable, but to be collected during year 1 of demo implementation | Eco-labelling and certification plan for each appropriate demo project location drafted | Eco-labelling and certification plans operational in at least two locations |
|  | 5 Waste management control mechanisms operational | Baseline information unavailable, but to be collected during year 1 of demo implementation | Waste management control mechanisms identified at the appropriate demo project sites | Waste management control mechanisms operational in at least two appropriate demo project sites |
| Outcome 2: Eco-tourism initiatives for alternative livelihoods and revenues developed for biodiversity conservation and local communities at relevant demo sites | 1. Management procedures & institutional support for developments in eco-tourism established | Not existing | Local civil society and government institutions to support eco-tourism developments identified at all demo sites | Local civil society / government institutions have management capacity support procedures for eco-tourism development in place in at least four demo projects |
|  | 2. Improved knowledge & information about eco-tourism within and around each demo site | Some baseline information is presented in the demo project narrative documents, additional information will be collected during year 1 of demo implementation | Locally appropriate information and media coverage being developed for eco-tourism services in at least four demo sites | Visitor resource centres and private sector investors are promoting local eco-tourism services in at least four demo projects |
|  | 3.Improved knowledge & information about HIV/AIDS and public health at each demo site (through working with partners competent in this field) | Baseline information is to be collected as part of the M&E framework development during year 1 of demo implementation | Information needs and capacity limitations to inform tourists and local communities on HIV/AIDS and public health understood | Appropriate information on HIV/AIDS and public health being shared locally at each demo project site |
|  | 4. Partnerships and networks of eco-tourism bodies and professionals formed | Some information has been provided in the demo project narratives, but this needs to be updated during year 1 of demo implementation | Forums and meetings are being organised to explore network formation/ strengthening opportunities at all demo sites | Network bodies have been formed and represent a growing membership of stakeholders in at least three demo project sites |
|  | 5. Evidence of stakeholders diversifying their eco-tourism activities and revenue sources at the demo sites | Some information has been provided in the demo project narratives, but this needs to be updated during year 1 of demo implementation | Data on eco-tourism facilities and services are being regularly collected at each demo project site | Analysis of data on eco-tourism operations completed for all demo project sites |
| Outcome 3: Improved reef recreation, management and monitoring mechanisms in place at relevant demo sites | 1. Survey and GIS mapping of sensitive areas and damaged sites completed | A number of previous projects have undertaken marine/reef mapping to a limited extent, and this information needs to be verified during year 1 of demo implementation | Survey work is actively on-going at all East African demo project sites | GIS maps showing areas of sensitivity and damage to biodiversity published for all East African demo project sites |
|  | 2. Procurement, installation, management of reef protection equipment as part of reef management strategy | As above | Reef management strategies being actively discussed by all appropriate East African demo projects and reef protection equipment being ordered | Reef management strategies with work plans and protection procedures in place in at least two East African demo project sites |
|  | 3. Awareness and Capacity Building (CB) on reef conservation being sustained by local stakeholders | Some information is provided in the demo project narrative documents, but this needs to be reviewed during year 1 of demo implementation | Appropriate stakeholders identified and awareness events and information on reef conservation being shared at all East African demo sites | Training and CB on reef conservation has been undertaken at all E African demo project locations and there is evidence of local stakeholder interest to maintain this |
|  | 4. Proposals for regulatory & institutional frameworks revised/established for reef area management at relevant sites in East Africa as a contribution to debates on improving regulatory mechanisms | Baseline information unavailable, but to be confirmed during year 1 of demo implementation | Appropriate locally based government agencies identified and the primary issues affecting reef areas being debated | Demo project experiences being used to inform appropriate locally based government agencies on improving reef management at all E African demo sites |